# PRE-PROPOSAL

- Project Title:

AI based System for Automated Report Generation from CBCT Scans for Tooth Implantation

- Project Duration:36 Months

- Project Summary:

The proposed system will be able to generate the automated medical reports for tooth implantation process. The input to the system will be considered as the CBCT (Cone Beam Computed Tomography) scans. The proposed system will reduce the requirement of sending these scans to the medical expert for the marking of different regions of interests. These regions further with the help of knowledge based system carried by the expert to conclude the implantation possibilities of the tooth under consideration. The major research questions addressed by the proposed system is the identification of upper and lower jaw from CBCT scans. Then the segmentation of tooth area and the bone area form these scans. With the help of artificial intelligence model these areas will be identified. For the quantitative assessment, different heights such as crest to sinus floor, crest to IAN floor etc. will be calculated. These quantitative values further will help in the qualitative analysis of tooth and bone by considering Lekholm & Zarb and Misch classifications. The major challenges involved in this work are the collection of CBCT scans, Segmentation of various region of interests, identification of the specific section of the CBCT data to make observations regarding the quantitative measures. AI based model is also required to deal with the automatic generation of reports. The automatic generation of medical report without the intervention of clinician or doctor from the CBCT dental scans is the novel aspect associated with the proposed system. The segmentation of specific point of interest such as crest, nasal floor, IAN canal etc. leads to the selection of appropriate level of also leads to the level of Lekholm & Zarb and Misch classifications. This further help in the generation of a summary report which will be easily understandable by the  patients and their family members.

- Keywords:

CBCT Scans, Dentistry, Lekholm & Zarb, Misch, Automated medical reports

- Objectives of the Project (in bullets) :

- Data Acquisition and Pre-Processing

- Model Development and Training

- User Study and Evaluation

- Dissemination and Reporting

# Novelty & Significance

- Automated generation of patient-friendly summaries of dental CBCT reports

- A novel approach for the identification of heights at crest, nasal floor, IAN canal to check the possibility of implantation.

- Reduction in the data labeling cost by active learning

- Output reports support both quantitative and qualitative parameters

- Preliminary work done, if any: NA

# Research Methodology(600 words)

The following interrelated phases will be used to carry out the project:

Phase-1: Data Acquisition: The collection of CBCT scans and reports is required to be done in this phase. This is the most crucial phase of the proposed project. The first milestone in this phase is make an agreement with the medical clinician or the data center from which the CBCT scans needs to be collected. Milestone-II of this phase is to collect 1200 CBCT scans of different patient which fall under the different levels of lekholm and zarb or Mich classifications. This phase also deals with the pre-processing task on these collected scan to handle the issue of poisonous noise, Thermal noise and the Ring Artifacts produced during the scanning process under CBCT scans.

Phase-2: Model Development and Training: During this phase we will develop a model to deal with the process of segmentation and identification of the different regions of interests. The segmentation needs to be done to locate the regions of lower jaw and upper jaw means Mandible and Maxilla. After that the segmentation needs to be carried out at the level of tooth identification and bone density identification. The Milestone-1 in this phase deals with the implementation of self training algorithm to extract the regions of Mandible and Maxilla. After this the identification of tooth under consideration along with the information about its particular section in CBCT scan is performed. Milestone-2 under this phase is to train the system over CBCT reports considered for the training phase. Milestone-3 under phase-2 is to evaluate the model as per different validation sets.

Phase-3: User study and Evaluation: This phase is involved with the evaluation part of identified points in tooth and bone regions such as Nasal Floor, IAN Cannel, Crest regions. This first milestone is to find out the quantitative measures as the heights form crest to nasal floor, crest to IAN floor etc. These heights and the desired sections of the tooth under consideration will be identified. The milestone-2 in this phase is to extract the information about the qualitative measures like lekholm and zarb or Mich classifications. This leads to the idea about the qualitative measure of the bone quality to find the status of the implantation process or the possibility of the implantation.

Phase-4: Dissemination and Reporting: This phase is involved with the writing of the final report after the compilation of all the results and findings. This process involved with the publication of articles related to the findings of different phases for the sake of approval from the publishing agencies and exposure of the findings to the outside word.

# GANT/PERT Chart for the project with timelines for the proposed duration

(UploadJpegimagemaxfilesize250KB)

| Phases | Year-1 | Year-2 | Year-3 |
| --- | --- | --- | --- |
| Phase-1: Data Acquisition | Q1-Q4 | Q1-Q2 | Q1-Q2 |
| Phase-2: Model Development and Training | Q3-Q4 | Q1-Q3 |  |
| Phase-3: User study and Evaluation |  | Q1-Q4 | Q1-Q4 |
| Phase-4: Dissemination and Reporting |  | Q4 | Q1-Q4 |

- Technology Readiness Level (TRL) of the project: At the ‘beginning of the project’ and expected to be at the ‘end of the project’

The proposed project spans TRL-1 to TRL-4 over the time of its execution with the focus of developing model, identifying parameters through experimentation

| TRL Level | Description | Planned Activity |
| --- | --- | --- |
| TRL-1 | Formulation of idea to handle the issue of automatic report generation. | Literature review, research gaps identification, identification of different challenges involved and the causes of the identified gaps. |
| TRL-2 | Analytical and Experimental proofs of the concept | How to train the system under consideration with the collected CBCT scans |
| TRL-3 | Technological Validations over Test Set | Testing of the scanned reports against the stored opinions of the experts of clinicians |
| TRL-4 | Technological Validation in real time scenario | To provide the CBCT scans to the proposed system which are not the part of dataset used for training and testing and evaluate the outcomes from clinicians or experts |

- Expertise of PI:

Principal Investigator : Prof. (Dr.) Gurpreet Singh

Papers:

- Singh, G., Sachan, M.K. An Unconstrained and Effective Approach of Script Identification for Online Bilingual Handwritten Text. Natl. Acad. Sci. Lett. 43, 453–456 (2020). https://doi.org/10.1007/s40009-020-00889-0

- R. Kaur and G. Singh, "Performance Comparison of AI Models for Digital Image captioning," 2022 International Conference on Computational Modelling, Simulation and Optimization (ICCMSO), Pathum Thani, Thailand, 2022, pp. 257-261, doi: 10.1109/ICCMSO58359.2022.00058.

- Singh, G., & Singh, B. (2011). Feature based method for human facial emotion detection using optical flow based analysis. An International Journal of Engineering Sciences, 4(1), 363-372.

- Sekhon, N.K., Singh, G. (2023). Hybrid Technique for Human Activities and Actions Recognition Using PCA, Voting, and K-means. In: Gupta, D., Khanna, A., Hassanien, A.E., Anand, S., Jaiswal, A. (eds) International Conference on Innovative Computing and Communications. Lecture Notes in Networks and Systems, vol 492. Springer, Singapore. https://doi.org/10.1007/978-981-19-3679-1_27

- Verma, Divya, Gurpreet Singh and Hatesh Shyan. "Multilayer Convolutional Neural Network for Plant Diseases Detection." International Journal of Engineering and Advanced Technology (IJEAT) 9.5 (2020).

- R. Kaur and G. Singh, "Automatic Image Captioning for Medical Diagnosis Report Generation," 2023 11th International Conference on Intelligent Systems and Embedded Design (ISED), Dehradun, India, 2023, pp. 1-6, doi: 10.1109/ISED59382.2023.10444545.

Patent:

- Singh, J. P., Singh, S., Kusla, V., Singh, G., Mittal, S., Kaur, R., & Mamta. (2023). Development of wireless resource and computation offloading for enhanced energy efficiency in the Internet of Vehicles (IoV). Indian Patent Application No. 202311061436. Filed 12 September 2023. Published 13 October 2023.

- Gaur, P. K., Kaundal, M., Sharma, A., Singh, G., Bhatia, V., & Chauhan, R. S. (2021). Air bag for train [Design registration]. Design No. 354845-001. Registered 12 December 2021. India.

- List of projects implemented/ being implemented by the investigator(list all). NA

| Project Title | Funding Agency | Duration | Sanction Cost | PIs/Co-PI name |
| --- | --- | --- | --- | --- |
| -- | -- | -- | -- | -- |

# Details of collaboration, if any: NA

Collaborator/sName,Roleintheproject,Institute,Budgetrequirement(ifany), Justification for budget requirement

| Name& Affiliation | Role in the project | Institute | Budget requirement | Justification |
| --- | --- | --- | --- | --- |
| -- | -- | -- | -- | -- |

- Expected outcome of the proposal:

The outcomes of this project are expected to the auto generated medical reports from the CBCT scans of dentistry. These scans are used during the process of tooth implantation. These reports provide a kind of idea to the doctor regarding the status that a specific tooth implant is possible or not. This will be done by the quantitative as well as qualitative assessment of tooth and associated bone. During this project the following outcomes are expected.

- New pre-processing algorithms to deal with special type of noises such as poisonous, thermal and ring artifacts

- New approach to automate the process of segmentation both at the level of tooth and bone.

- Region identification algorithms for accessing bone and tooth quality

- Automated generation of medical report from the CBCT Scan

- High Impact research publications

# Total Budget proposed for the project:

Budget (Recurring + Nonrecurring):

A1: Manpower

| S.No. | Position | Consolidated emolument | Year-1 | Year-2 | Year-3 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | JRF (1) | Rs. 37,000 pm+8% HRA for first two years. 42,000 +8% HRA for 3rd year | 479520 | 479520 | 544320 | 15,03,360 |

A2: Consumable

| S.No. | Head | Year-1 | Year-2 | Year-3 | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Software licenses (Image processing e.g., MATLAB, 3D Slicer plugins, Python libs) | 50000 | 30000 | 20000 | 1,00,000 |
| 2 | Dental CBCT dataset acquisition | 50000 | 30000 | 20000 | 1,00,000 |
| 3 | Storage devices (External HDD / SSD for data backup) | 10,000 | NIL | NIL | 10000 |
| 4 | Miscellaneous (printing, stationary) | 5000 | 5,000 | 5000 | 15000 |
|  | Total | 1,15,000 | 65000 | 45000 | 2,25,000 |

A3: Other Items

| S.No. | Head | Year-1 | Year-2 | Year-3 | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Conferences/Workshops | 100000 | 100000 | 100000 | 3,00,000 |
| 2 | Contingency | 50000 | 50000 | 50000 | 1,00,000 |
|  | Total | 1,50,000 | 1,50,000 | 1,50,000 | 4,50,000 |

A4: Equipments=NIL

Total: A1+A2+A3+A4= Rs. 21,78,360

Justification of Budget:

- JRF Salary: As per typical government fellowship norms in India (adjust as per institute).

- Dataset: Either purchase, license, or collect your own annotated CBCT scans.

- Software: Use open-source tools where possible to reduce costs, but budget for licenses if proprietary software (Image processing e.g., MATLAB, 3D Slicer plugins, Python libs) is needed.

- Storage Device: For backup purpose (One time purchase is required)

- Travel: For dissemination and knowledge exchange.

- Contingency: Always budget for ~5-10% unexpected costs.