# PRE-PROPOSAL

- Project Title:

AI based System for Automated Report Generation from CBCT Scans for Tooth Implantation

- Project Duration:36 Months

- Project Summary:

CBCT scans for tooth implantation assessment performs a vital role. These scans are able to present the three dimensional (3D) view of these images. The details present in these scans are able to assess the quality of the bone and the tooth under consideration. After capturing, these CBCT images, there is a requirement of the attention of an expert to proceed further. The role of the expert is to identify different points in the image such as Crest, IAN Canal, Nasal Floor etc. These points further helps in the generation of idea abort the quantitative parameter i.e. heights among these located points. These heights further used to extract the idea about the different levels of Lekholm & Zarb and Misch classifications. Here, the unavailability of the expert may cause the overall delay in this process. The proposed system have the ability to generate the automated medical reports for tooth implantation process. The input to the system will be considered as the CBCT (Cone Beam Computed Tomography) scan. The proposed system will provide an aid to the medical expert or clinitions for the marking of different regions of interests. These regions further with the help of knowledge based system will provide the idea about the possibilities of the tooth implantation process. The major research questions addressed here is the identification of upper jaw, lower jaw, tooth area and the bone area during the segmentation process. 3D-UNET model will be used for the identification of these regions. For the quantitative assessment, different heights such as crest to sinus floor, crest to IAN floor etc. will be calculated. These values further will help in the qualitative analysis of tooth and bone by considering Lekholm & Zarb and Misch classifications. The major challenges involved in this work are the collection of CBCT scans, segmentation of various region of interests, identification of the specific section of the CBCT data to make observations regarding the quantitative measures. The automatic generation of medical report to provide support to clinician or doctor from the CBCT dental scans is the novel aspect associated with the proposed system. This further help in the generation of a summary report which will be easily understandable by the  patients and their family members.

- Keywords:

CBCT Scans, Dentistry, Lekholm & Zarb, Misch, Automated medical reports

- Objectives of the Project:

- To prepare and annotate a dataset of 1200 anonymized CBCT scans, with strong agreement between experts (κ > 0.85) on key features like the Mandibular canal and maxillary sinus Model Development and Training

- Model Development and Training by using 3D-Unet model for the segmentation and identification of the different regions of interests. The segmentation needs to be done to locate the regions of lower jaw and upper jaw means Mandible and Maxilla. The expected Dice score for this part will be >0.92 along with BLEU score >.80.

- User study and Evaluation to identifyy points in tooth and bone regions such as Nasal Floor, IAN Cannel, Crest regions. These points helps in the extraction of qualitative measures like Lekholm and Zarb or Mich classifications

- Dissemination and Reporting for the writing of the final report after the compilation of all the results and findings.

# Novelty & Significance

- Automated generation of patient-friendly summaries of dental CBCT reports

- A novel approach for the identification of heights at crest, nasal floor, IAN canal to check the possibility of implantation.

- Reduction in the data labeling cost by active learning

- Output reports support both quantitative and qualitative parameters

- Preliminary work done, if any: NA

# Research Methodology

The following interrelated phases will be used to carry out the project:

Phase-1: To prepare and annotate a dataset of 1200 anonymized CBCT scans, with strong agreement between experts (κ > 0.85) on key features like the Mandibular canal and maxillary sinus. This phase also deals with the pre-processing task on these collected scan to handle the issue of poisonous noise, thermal noise and the ring artifacts produced during the scanning process.

Phase-2: Model Development and Training: This phase will be involved in the application of 3D-Unet model for the segmentation and identification of the different regions of interests. The segmentation needs to be done to locate the regions of lower jaw and upper jaw means Mandible and Maxilla. The expected Dice score for this part will be >0.92. After that the segmentation needs to be carried out at the level of tooth identification and bone desnsity identification. The Milestone-1 in this phase deals with the implementation of self training algorithm to extract the regions of Mandible and Maxilla. After this the identification of tooth under consideration along with the information about its particular section in CBCT scan is performed. Milestone-2 under this phase is to train the system over CBCT reports considered for the training phase. Milestone-3 under phase-2 is to evaluate the model as per different validation sets. The BLEU score for this phase must be >0.80.

Phase-3: User study and Evaluation: This phase is involved with the evaluation part of identified points in tooth and bone regions such as Nasal Floor, IAN Cannel, Crest regions. This first milestone is to find out the quantitative measures as the heights form crest to nasal floor, crest to IAN floor etc. These heights and the desired sections of the tooth under consideration will be identified. The milestone-2 in this phase is to extract the information about the qualitative measures like Lekholm and Zarb or Mich classifications. This leads to the idea about the qualitative measure of the bone quality to find the status of the implantation process or the possibility of the implantation.

Phase-4: Dissemination and Reporting: This phase is involved with the writing of the final report after the compilation of all the results and findings. This process involved with the publication of articles related to the findings of different phases for the sake of approval from the publishing agencies and exposure of the findings to the outside word.

# GANT/PERT Chart for the project with timelines for the proposed duration

| Phase | Task | Year-1 | Year-2 | Year-3 |
| --- | --- | --- | --- | --- |
| Data Acquisition | Ethical Approval | Q1 |  |  |
|  | Data sharing Agreement | Q1-Q2 |  |  |
|  | Designing Collection Protocol | Q2 |  |  |
|  | Data Collection (Pilot) | Q3 |  |  |
|  | Data Collection Full | Q4 |  |  |
|  | Data Anonymization |  | Q1-Q4 | Q1-Q2 |
| Model Development and Training | Prototype Model | Q4 | Q1 |  |
|  | Optimizing Architecture |  | Q2 |  |
|  | Training on Full dataset |  | Q3-Q4 |  |
|  | Validation & Testing |  |  | Q1-Q2 |
| User study and Evaluation | Design of Study Protocol |  |  | Q1 |
|  | Approval and Cosent from Institute |  |  | Q1 |
|  | User Study (pilot) |  |  | Q2 |
|  | User Study Full Scale |  |  | Q3-Q4 |
| Reporting | Interim Reporting & Feedback |  |  | Q1 |
|  | Final Reporting and Publications |  |  | Q3-Q4 |

- Technology Readiness Level (TRL) of the project: At the ‘beginning of the project’ and expected to be at the ‘end of the project’

The proposed project spans TRL-1 to TRL-4 over the time of its execution with the focus of developing model, identifying parameters through experimentation

| TRL Level | Description | Planned Activity |
| --- | --- | --- |
| TRL-1 | Formulation of idea to handle the issue of automatic report generation. | Literature review, research gaps identification, identification of different challenges involved and the causes of the identified gaps. |
| TRL-2 | Analytical and Experimental proofs of the concept | How to train the system under consideration with the collected CBCT scans |
| TRL-3 | Technological Validations over Test Set | Testing of the scanned reports against the stored opinions of the experts of clinicians |
| TRL-4 | Technological Validation in real time scenario | To provide the CBCT scans to the proposed system which are not the part of dataset used for training and testing and evaluate the outcomes from clinicians or experts |

- Expertise of PI:

Principal Investigator : Prof. (Dr.) Gurpreet Singh

Worked on various AI and Image processing projects. The projects include " Ant Colony based approach to detect the boundary of barain tumour ", "Human emotion detection system from facial image dataset",  "Online conversion of bilingual handwritten data to digital output".Some of the publications are mentioned below.

Papers:

- Singh, G., Sachan, M.K. An Unconstrained and Effective Approach of Script Identification for Online Bilingual Handwritten Text. Natl. Acad. Sci. Lett. 43, 453–456 (2020). https://doi.org/10.1007/s40009-020-00889-0

- R. Kaur and G. Singh, "Performance Comparison of AI Models for Digital Image captioning," 2022 International Conference on Computational Modelling, Simulation and Optimization (ICCMSO), Pathum Thani, Thailand, 2022, pp. 257-261, doi: 10.1109/ICCMSO58359.2022.00058.

- Singh, G., & Singh, B. (2011). Feature based method for human facial emotion detection using optical flow based analysis. An International Journal of Engineering Sciences, 4(1), 363-372.

- Sekhon, N.K., Singh, G. (2023). Hybrid Technique for Human Activities and Actions Recognition Using PCA, Voting, and K-means. In: Gupta, D., Khanna, A., Hassanien, A.E., Anand, S., Jaiswal, A. (eds) International Conference on Innovative Computing and Communications. Lecture Notes in Networks and Systems, vol 492. Springer, Singapore. https://doi.org/10.1007/978-981-19-3679-1_27

- Verma, Divya, Gurpreet Singh and Hatesh Shyan. "Multilayer Convolutional Neural Network for Plant Diseases Detection." International Journal of Engineering and Advanced Technology (IJEAT) 9.5 (2020).

- R. Kaur and G. Singh, "Automatic Image Captioning for Medical Diagnosis Report Generation," 2023 11th International Conference on Intelligent Systems and Embedded Design (ISED), Dehradun, India, 2023, pp. 1-6, doi: 10.1109/ISED59382.2023.10444545.

Patent:

- Singh, J. P., Singh, S., Kusla, V., Singh, G., Mittal, S., Kaur, R., & Mamta. (2023). Development of wireless resource and computation offloading for enhanced energy efficiency in the Internet of Vehicles (IoV). Indian Patent Application No. 202311061436. Filed 12 September 2023. Published 13 October 2023.

- Gaur, P. K., Kaundal, M., Sharma, A., Singh, G., Bhatia, V., & Chauhan, R. S. (2021). Air bag for train [Design registration]. Design No. 354845-001. Registered 12 December 2021. India.

- List of projects implemented/ being implemented by the investigator(list all). NA

| Project Title | Funding Agency | Duration | Sanction Cost | PIs/Co-PI name |
| --- | --- | --- | --- | --- |
| -- | -- | -- | -- | -- |

# Details of collaboration, if any: NA

Collaborator/sName,Roleintheproject,Institute,Budgetrequirement(ifany), Justification for budget requirement

| Name& Affiliation | Role in the project | Institute | Budget requirement | Justification |
| --- | --- | --- | --- | --- |
| -- | -- | -- | -- | -- |

- Expected outcome of the proposal:

The outcomes of this project are expected to the auto generated medical reports from the CBCT scans of dentistry. These scans are used during the process of tooth implantation. These reports provide a kind of idea to the doctor regarding the status that a specific tooth implant is possible or not. This will be done by the quantitative as well as qualitative assessment of tooth and associated bone. During this project the following outcomes are expected.

- Pre-processing algorithms (Poisonous Noise Removal, Thermal Noice Removal to and Ring Artifacts remoal)  Will be introduced to improve quality of the input data.

- Ssegmentation algorithms for both tooth and bone segmentation.

- Region identification algorithms for accessing bone and tooth quality

- Automated generation of medical report from the CBCT Scan

- High Impact research publications

# Total Budget proposed for the project:

Budget (Recurring + Nonrecurring):

A1: Manpower

| S.No. | Position | Consolidated emolument | Year-1 | Year-2 | Year-3 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | JRF (1) | Rs. 37,000 pm+8% HRA for first two years. 42,000 +8% HRA for 3rd year | 479520 | 479520 | 544320 | 15,03,360 |

A2: Consumable

| S.No. | Head | Year-1 | Year-2 | Year-3 | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Software Licenses (e.g., MATLAB, Python libs) | 50000 | 30000 | 20000 | 100000 |
| 2 | Dental CBCT Dataset (incl. ethics, annotation) | 60000 | 40000 | 20000 | 120000 |
| 3 | Cloud Storage / External HDDs (4TB x 2) | 15000 | 5000 | 5000 | 25000 |
| 4 | Printing & Stationary | 5000 | 5000 | 5000 | 15000 |
| 5 | Radiologist/Expert Annotation Fees | 40000 | 30000 | 20000 | 90000 |
| 6 | Ethics Committee & Patient Consent Processing | 10000 | 5000 | 5000 | 20000 |
|  | Total | 1,80,000 | 1,15,000 | 75,000 | 3,70,000 |

A3: Other Items

| S.No. | Head | Year-1 | Year-2 | Year-3 | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Conferences/Workshops | 100000 | 100000 | 100000 | 3,00,000 |
| 2 | Contingency | 50000 | 50000 | 50000 | 1,00,000 |
|  | Total | 1,50,000 | 1,50,000 | 1,50,000 | 4,50,000 |

A4: Equipments:

| S.No. | Item | Estimated Cost |
| --- | --- | --- |
| 1 | High-performance Workstation with GPU (e.g., NVIDIA RTX 4090, 128GB RAM, 4TB SSD) | 4,50,000 |

Total: A1+A2+A3+A4= Rs. 27,73,360

Justification of Budget:

- JRF Salary: As per typical government fellowship norms in India (adjust as per institute).

- Dataset: Either purchase, license, or collect your own annotated CBCT scans.

- Software: Use open-source tools where possible to reduce costs, but budget for licenses if proprietary software (Image processing e.g., MATLAB, 3D Slicer plugins, Python libs) is needed.

- Storage Device: For backup purpose (One time purchase is required)

- Travel: For dissemination and knowledge exchange.

- Contingency: Always budget for ~5-10% unexpected costs.